# Appendix I: Legislation Process - Checklist

The following checklist is provided to assist officers in the legislation process. It provides a brief overview of what you need to do to get your bill on to the legislation programme and through the Parliament. Further details can be found in the Legislation Handbook.

# Developing your Legislation Proposal

☐	Is legislation required?

☐	Secure ministerial approval

☐	Consult within your department and other relevant Commonwealth agencies

☐	Check the Impact Analysis (IA) requirements with the Office of Impact Analysis

☐	Is the proposal consistent with international obligations under human rights instruments?

☐	Seek policy authority—Cabinet / Prime Minister / relevant ministers

☐	Issue drafting instructions to the Office of Parliamentary Counsel (OPC) for primary legislation and, if necessary, associated subordinate legislation

Consider draft bill and instruct OPC further, if required

☐	Get on the legislation program—lodge a bid for the next sittings or seek to vary the program for the current sittings

Parliamentary Business Committee considers requests to add bills to the program and accords priority

☐	Consult within your department and other relevant Commonwealth agencies on draft bill

☐	Seek Prime Minister’s approval if you wish to provide draft legislation outside the Commonwealth—states / territories / key stakeholders / public

☐	Do you need to seek further policy authority as a result of the consultation or drafting process?

☐	Bill is settled with OPC

# Finalising your Legislation – Immediately prior to proposed Introduction

☐	Prepare explanatory memorandum

include a Statement of Compatibility with Human Rights and, if required, an IA

☐	Prepare second reading speech

☐	Complete Legislation Overview sent by Legislation Section, which seeks advice on the bill—i.e. status of policy approval, ministerial agreements, etc.

Legislation Overview sent two weeks before proposed introduction

☐	Seek minister’s approval of bill, explanatory memorandum and second reading speech

☐	Electronically lodge explanatory memorandum with Legislation Section in PM&C

deadline of 11.00 am on Wednesday of week before proposed introduction

☐	Advise PM&C when minister has approved bill and explanatory memorandum

deadline of 11.00 am on Friday of week before proposed introduction

☐	Prepare briefing for party clearance processes and send to minister’s office

if requested by minister, attend party meetings

☐	Legislation is approved for introduction at legislation approval process meeting—generally held Monday morning of week of proposed introduction

☐	Legislation receives party clearance—generally held Tuesday morning of week of proposed introduction

☐	Print bulk copies of explanatory memorandum and second reading speech and lodge with Parliament House

at least one sitting day before proposed introduction

☐	Prepare briefing folders and submit to minister’s office

☐	Follow up on any outstanding agreements and provide copies to PM&C (via LLO)

all relevant departments and/or ministers must provide written agreement to the legislation before a bill can be introduced

☐	Bill is introduced

# Passage of your Legislation through Parliament

☐	Monitor progress of legislation—e.g. timing of debate, examination by Senate Standing Committee for the Scrutiny of Bills and Parliamentary Joint Committee on Human Rights, referral to committees

☐	If necessary, respond to report(s) of Senate Standing Committee for the Scrutiny of Bills and/or Parliamentary Joint Committee on Human Rights

minister may need to write to relevant committee(s) to address concerns; explanatory memorandum may require an addendum or a correction

☐	If government amendments proposed:

Brief minister—prepare correspondence seeking policy authority from Prime Minister and/or other relevant ministers

Issue drafting instructions to OPC and settle text of amendments

Prepare supplementary explanatory memorandum

Electronically lodge supplementary explanatory memorandum with Legislation Section of PM&C

Seek party clearance and, if requested by minister, attend party meetings

Submit final papers to minister for approval, including provision of speaking notes

Advise PM&C (via LLO) when minister has approved amendments for introduction

☐	Amendments are approved for introduction at legislation approval process meeting

☐	Amendments receive party clearance

☐	If the Government intends to accept non-government amendments:

Consult OPC on the proposed amendments to ensure legislation will still operate as intended

Brief minister—prepare correspondence seeking policy authority from Prime Minister

☐	Bill debated and passed in first chamber

☐	If bill was amended in first chamber (either government or non-government amendments), prepare revised explanatory memorandum and, if required, a new second reading speech

☐	Update legislation briefing folders for your minister

☐	Monitor progress of legislation—further government amendments may be required

☐	Bill debated and passed in second chamber

☐	If bill was amended in second chamber, amendments are returned to first chamber for consideration

☐	Same version of bill passes both chambers

☐	Check for Royal Assent (via LLO)

If required, prepare proclamation papers and subordinate legislation for consideration by Executive Council